## Issues
| Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | In Progress | Google Firebase Login | I | Calendar Authorization Fails | Google Firebase | 2017-04-24 | 2017-04-28 | 2017-04-24 | Unresolved - Needs Work
2 | New | Settings Menu Login | A | Building |  | 2017-04-24 |  | 2017-04-24
3 | Completed | User Interface | A | Redesign icon for the Application | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
4 | Completed | User Interface | A | Design vector graphic for iconless event | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
5 | Completed | User Interface | A | Update UI to match color theme | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
6 | New | User Interface | A | Design Drop Down Calendar Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
7 | New | User Intergace | A | Design Groups List Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
8 | New | User Interface | A | Design Settings List Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
9 | New | User Interface | A | Optimise UI XML files | Android Application | 2017-04-24 | 2017-05-05 | 2017-04-24 | Dependant on all other UI files
10 | New | User Interface | A | Profile Picture in Event Creation | Android Application | 2017-04-24 | 2017-05-09 | 2017-04-24 | No dependencies
11 | Completed | Google Firebase Login | A | Connect Application to Firebase | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
12 | New | Google Firebase Login | A | Add code to |  | 2017-04-24 |  | 2017-04-24 | Available for Completion
13 | Completed | Google Firebase Login | A | Learn Firebase console | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
14 | Completed | Google Firebase Login | A | Setup Firebase Login | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
15 | New | Google Firebase Login | A | Build data structure for Firebase | Google Firebase | 2017-04-24 |  | 2017-04-24 | Completed by Michael and Dylan
16 | Completed | Google Firebase Login | A | Implement crash reporting libraries | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
17 | New | Google Firebase Login and Android Application | A | Local cache storage for offline app usage | Google Firebase, Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24 | Dependent on Firebase database completely being finished
18 | New | Google Firebase Login | A | Non-Google Logins | Google Firebase | 2017-04-24 | TBA | 2017-04-24 | Dependent on the rest of the application being finished
19 | New | Android Application | A | Settings Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 8
20 | New | Android Application | A | Groups Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 7
21 | New | Android Application | A | Friends Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 6
22 | New | Android Application | A | Calendar Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 6
23 | Completed | Android Application | I | Broken Add Event page | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael and Dylan
24 | Completed | Google Firebase | I | User Login with Firebase Integration | Android Studio, Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael and Dylan
25 | New | Android Application | A | Synchronize Add Event page return values with data structure | Android Studio, Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24
26 | New | Android Application | A | Optimise Included Libraries for application libraries | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
27 | New | Android Application | A | Optimise functions for RAM usage and general speed | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
28 | New | Android Application | A | Implement all UI changes done in UI task | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
29 | In Progress | Google Forms | A | Pre-Distribution Questionnaire | Google Forms | 2017-04-24 | 2017-04-24 | 2017-04-24
30 | In Progress | Android Application | A | Usability Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
31 | In Progress | Android Application | A | Component Performance Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
32 | Completed | User Testing | A | Focus Group Designation | Google Forms | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Rocco
33 | New | User Testing | A | Mass Distribution with PKA | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24
34 | In Progress | Android Application | A | Java Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
35 | In Progress | Android Application | A | XML Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
36 | In Progress | Android Application | A | Integration Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
37 | New | User Testing | A | Post-Distribution Questionnaire | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete