## Issues
| Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | In Progress | Google Firebase Login | I | Calendar Authorization Fails | Google Firebase | 2017-04-24 | 2017-04-28 | 2017-04-24 | Unresolved - Needs Work
2 | New | Settings Menu Login | A | Building |  | 2017-04-24 |  | 2017-04-24
6 | New | User Interface | A | Design Drop Down Calendar Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
7 | New | User Intergace | A | Design Groups List Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
8 | New | User Interface | A | Design Settings List Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
9 | New | User Interface | A | Optimise UI XML files | Android Application | 2017-04-24 | 2017-05-05 | 2017-04-24 | Dependant on all other UI files
10 | New | User Interface | A | Profile Picture in Event Creation | Android Application | 2017-04-24 | 2017-05-09 | 2017-04-24 | No dependencies
25 | New | Android Application | A | Synchronize Add Event page return values with data structure | Android Studio, Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24
27 | New | Android Application | A | Optimise functions for RAM usage and general speed | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
28 | New | Android Application | A | Implement all UI changes done in UI task | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
12 | New | Google Firebase Login | A | Add code to |  | 2017-04-24 |  | 2017-04-24 | Available for Completion
17 | New | Google Firebase Login and Android Application | A | Local cache storage for offline app usage | Google Firebase, Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24 | Dependent on Firebase database completely being finished
18 | New | Google Firebase Login | A | Non-Google Logins | Google Firebase | 2017-04-24 | TBA | 2017-04-24 | Dependent on the rest of the application being finished
19 | New | Android Application | A | Settings Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 8
20 | New | Android Application | A | Groups Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 7
21 | New | Android Application | A | Friends Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 6
22 | New | Android Application | A | Calendar Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 6
33 | New | User Testing | A | Mass Distribution with PKA | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24
34 | In Progress | Android Application | A | Java Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
35 | In Progress | Android Application | A | XML Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
36 | In Progress | Android Application | A | Integration Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
37 | New | User Testing | A | Post-Distribution Questionnaire | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24
31 | In Progress | Android Application | A | Component Performance Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
30 | In Progress | Android Application | A | Usability Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete