## Issues
| Status | Associated Design Entity | Issue Type | Brief Description | Resource
1 | Completed | Google Firebase Login | A | Setup Firebase Login | Google Firebase
2 | Completed | User Interface | A | Redesign icon for the Application | Android Application
3 | Completed | User Interface | A | Design vector graphic for iconless event | Android Application
4 | Completed | User Interface | A | Update UI to match color theme | Android Application
5 | Completed | User Interface | A | Design Groups List Interface | Android Application
6 | Completed | User Interface | A | Design Settings List Interface | Android Application
7 | Completed | Google Firebase Login | A | Connect Application to Firebase | Android Application
8 | Completed | User Interface | A | Optimise UI XML files | Android Application
9 | Completed | Google Firebase Login | A | Learn Firebase console | Google Firebase
10 | Completed | Google Firebase Login | A | Implement crash reporting libraries | Google Firebase
11 | Completed | Google Firebase Login and Android Application | A | Local cache storage for offline app usage | Google Firebase, Android Studio
12 | Completed | Android Application | I | Broken Add Event page | Android Studio
13 | Completed | Google Firebase | I | User Login with Firebase Integration | Android Studio, Google Firebase
14 | Completed | Android Application | A | Optimise Included Libraries for application libraries | Android Studio
15 | Completed | Google Forms | A | Pre-Distribution Questionnaire | Google Forms
16 | Completed | User Interface | A | Profile Picture in Event Creation | Android Application
5 | Completed | Android Application | A | Synchronize Add Event page return values with data structure | Android Studio, Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete