## Issues
| Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | In Progress | Google Firebase Login | I | Calendar Authorization Fails | Google Firebase | 2017-04-24 | 2017-04-28 | 2017-04-24 | Unresolved - Needs Work
2 | New | Settings Menu Login | A | Building |  | 2017-04-24 |  | 2017-04-24
3 | New | User Interface | A | Design Drop Down Calendar Interface | Android Application | 2017-04-24 | 2017-04-28 | 2017-04-24 | Available for Completion
16 | New | User Testing | A | Post-Distribution Questionnaire | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24
6 | New | Android Application | A | Optimise functions for RAM usage and general speed | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
12 | New | User Testing | A | Mass Distribution with PKA | Google Forms | 2017-04-24 | 2017-05-29 | 2017-04-24 | Dependent on 6
11 | New | Android Application | A | Calendar Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 6
8 | In Progress | Android Application | A | Settings Page Implementation | Android Studio | 2017-04-24 | 2017-04-24
9 | In Progress | Android Application | A | Groups Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 8
10 | In Progress | Android Application | A | Friends Page Implementation | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Dependent on 7
13 | Ongoing | Android Application | A | Java Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
14 | Ongoing | Android Application | A | XML Component Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
15 | Ongoing | Android Application | A | Integration Testing | Android Studio | 2017-04-24 | 2017-05-16 | 2017-04-24
17 | Ongoing | Android Application | A | Component Performance Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
4 | Ongoing | User Interface | A | Optimise UI XML files | Android Application | 2017-04-24 | 2017-05-05 | 2017-04-24 | Dependant on all other UI files
18 | Ongoing | Android Application | A | Usability Testing | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
7 | Ongoing | Android Application | A | Implement all UI changes done in UI task | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
19 | Pending | Google Firebase Login | A | Non-Google Logins | Google Firebase | 2017-04-24 | TBA | 2017-04-24

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete