## Issues
| Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
14 | Completed | Google Firebase Login | A | Setup Firebase Login | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
3 | Completed | User Interface | A | Redesign icon for the Application | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
4 | Completed | User Interface | A | Design vector graphic for iconless event | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
5 | Completed | User Interface | A | Update UI to match color theme | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael Rinehart
11 | Completed | Google Firebase Login | A | Connect Application to Firebase | Android Application | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
13 | Completed | Google Firebase Login | A | Learn Firebase console | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
16 | Completed | Google Firebase Login | A | Implement crash reporting libraries | Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed
23 | Completed | Android Application | I | Broken Add Event page | Android Studio | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael and Dylan
24 | Completed | Google Firebase | I | User Login with Firebase Integration | Android Studio, Google Firebase | 2017-04-24 | 2017-04-24 | 2017-04-24 | Completed by Michael and Dylan
26 | Completed | Android Application | A | Optimise Included Libraries for application libraries | Android Studio | 2017-04-24 | 2017-05-09 | 2017-04-24
29 | Completed | Google Forms | A | Pre-Distribution Questionnaire | Google Forms | 2017-04-24 | 2017-04-24 | 2017-04-24

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete